## RAID LOG
RAID Log
| Project title: | Intern Performance Analysis |  | Project Id: | IAC IP23 | Project Manager: | Harshada Topale
| DOCUMENT VERSION: | Raid Log |  | Last Updated date: | 2025-06-15 | Project Team Lead: | ABC
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Delays in maintenance may impact data accuracy, system performance, or project timelines. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High |  | Open | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical |  | Closed | Assumption
3 | [8 empty] | Issue
4 | [8 empty] | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24