## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0
Candidate Name | Yash Karande
PROJECT NAME | Data Analytics
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Data Analytics Job Portal
PROJECT SCOPE | Students Jobs Scope improvement
PROJECT START DATE | 2025-06-13
PROJECT END DATE | 2025-06-15
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 2.2 Baseline project plan |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 3.2 Build |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
| 3.2.1 Features |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
Student Dashboard
Graphs and visaualization
| Dashboard page layout |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
Key Indiactors
Advance key Indicatiors
Jobs
| Students |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
List of candidates with information
| Scope |  | 2025-06-13 | 2025-06-15 | 3 | COMPLETED
List of employers with information
| 3.3 Testing |  | 2025-06-13 | 2025-06-15 | 6 | COMPLETED
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2025-06-13 | 2025-06-15 | 1 | COMPLETED